## Tasks
task_id | task_name | assignee | status | priority | project | created_date | start_date | end_date | actual_duration | is_delayed | bottleneck_type | comments | reassignment_count
1 | Fix login bug | Alice | Completed | High | Website Revamp | 2024-01-01 | 2024-01-02 | 2024-01-05 | 3 | 0 | Process | Urgent issue | 1
2 | Update UI | Bob | In Progress | Medium | Website Revamp | 2024-01-03 | 2024-01-04 | 2024-01-07 | 2.5 | 1 | Tooling | Redesign needed | 0
3 | Optimize DB | Charlie | Not Started | Low | Backend Overhaul | 2024-01-02 |  |  |  | 0 |  |  | 0

## Bottlenecks
task_id | task_name | assignee | project | priority | bottleneck_type | severity_score | root_cause_suggestion | detected_date | actual_duration | is_delayed
2 | Update UI | Bob | Website Revamp | Medium | Tooling | 70 | UI tools were outdated | 2024-01-05 | 2.5 | 1
1 | Fix login bug | Alice | Website Revamp | High | Process | 85 | Lack of clarity in scope | 2024-01-03 | 3 | 0

## GPT_Suggestions
task_id | task_name | assignee | project | priority | suggestion_text | root_causes | recommendations | prompt_version | model_used | sentiment | urgency | quality_score | applied | applied_action | created_at | feedback_status | feedback_notes | feedback_date | was_helpful
2 | Update UI | Bob | Website Revamp | Medium | Change assignee | Wrong skillset | Assign to UI specialist | v2 | gpt-4 | Neutral | Medium | 75 | 0 |  | 2024-01-07 |  |  |  | 0
1 | Fix login bug | Alice | Website Revamp | High | Reduce task scope | Scope too broad | Limit scope to MVP | v2 | gpt-4 | Negative | High | 85 | 1 | Refined scope | 2024-01-05 | applied | Worked well | 2024-01-06 | 1

## Improvements
task_id | task_name | assignee | project | action_taken | owner | date_applied | impact_measured | improvement_score | improvement_percentage | current_status | currently_delayed
1 | Fix login bug | Alice | Website Revamp | Scope reduced | Team Lead | 2024-01-06 | Yes | 85 | 30 | Completed | 0

## Reassignments
task_id | task_name | project | from_assignee | to_assignee | reason | triggered_by | reassignment_date | was_delayed_before | is_delayed_after | current_status
2 | Update UI | Website Revamp | Bob | Diana | UI mismatch | Manual review | 2024-01-04 | 0 | 1 | In Progress

## ML_Predictions
task_id | task_name | assignee | project | model_type | predicted_duration | predicted_delay_prob | confidence_score | model_version | prediction_date | actual_outcome | prediction_correct | actual_duration | is_delayed
2 | Update UI | Bob | Website Revamp | RandomForest | 3 | 0.5 | 0.85 | v1.0 | 2024-01-02 | Delayed | 0 | 2.5 | 1
1 | Fix login bug | Alice | Website Revamp | XGBoost | 4.5 | 0.8 | 0.9 | v1.0 | 2024-01-01 | On Time | 1 | 3 | 0

## Summary_Metrics
total_tasks | avg_duration_days | delayed_count | delay_percentage | bottleneck_count | total_assignees | total_projects | completed_tasks | in_progress_tasks | export_timestamp
3 | 2.75 | 1 | 33.3333 | 2 | 3 | 2 | 1 | 1 | 2026-01-21T22:44:21.676539